## Cover Sheet for Guidance
Field Name | Field Guidance
ID | For new programs, please enter donor project ID
Title | For new programs, please enter project title
Implementing Agency | Please select an option from the dropdown menu. If your desired option is unavailable, you may enter using free text.
Amount in OC | Please enter the total grant/loan amount
Start Date | Please enter the start date of the grant using dd/mm/yyyy
Closing Date | Please enter the planned end date using dd/mm/yyyy
Sector | Please select an option from the dropdown menu.
Region | If the project is working at the region level, please copy/paste the UACS code for the appropriate region(s) from the "Locations_Reference" tab. Please use a comma to separate if there are multiple values. If the project is working at the province and/or municipal level, please leave blank.
Province | If the project is working at the province level, please copy/paste the UACS code for the appropriate province(s) from the "Locations_Reference" tab. Please use a comma to separate if there are multiple values. If the project is working at the municipal level, please leave blank.
City/Municipality | If the project is working at the municipal level, please copy/paste the UACS code for the appropriate municipality/ies from the "Locations_Reference" tab. Please use a comma to separate if there are multiple values.
Status | Dropdown
Cumulative Allotments | Please enter the total program-to-date allotments using the currency specified in the "Original Currency (OC)" field.
Cumulative Obligations | Please enter the total program-to-date obligations using the currency specified in the "Original Currency (OC)" field.
Total Disbursments Program-to-Date | Please enter the total program-to-date disbursements using the currency specified in the "Original Currency (OC)" field.
Target | Please enter the targeted physical completion % at the time of reporting
Actual | Please enter the actual physical completion % at the time of reporting
Issues | Please enter a description of any issues identified at this stage of implementation.
Issues Classification | Please enter the classification of issues based upon the list provided (INSERT)

## LFPP Dataset
CORE | CORE | CORE |  | CORE | CORE | CORE | CORE | CORE | CORE | CORE | CORE | FINANCIAL |  |  | PHYSICAL
ID | Title | Implementing Agency | Funding Institution | Amount in OC (PhP) | Start Date | Closing Date | Sector | Region | Province | City/Municipality | Status | Cumulative Allotment | Cumulative Obligations | Total Disbursements Program-to-Date | Target | Actual | Physical Performance (%) | Physical Status | Issues | Issues Classification
000004141100001 | PAyapa at MAsaganang PamayaNAn (PAMANA) | DA | Locally-funded | 4797 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 1844.223 | 1623.696 | 1011.582 | 303 | 23 | 16.8858 | Behind Schedule
162002000700000 | Agribusiness and Marketing Assistance Service (AMAS) Trading Center | DA | Locally-funded | 1351 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing |  |  |  | 7 | 7 | 100 | On-schedule
162003030600003 | National High Value Crops Development Program (HVCDP) | DA | Locally-funded | 2199.697 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 2336 | 1690.784 |  |  |  | 84.9142
DA001 | Agri-Pinoy Livestock Program | DA | Locally-funded | 1616.205 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 1685.164 | 989.642 | 424.34 | 198046 | 278620 | 77.5644 | Behind Schedule
162003030600001 | Agri-Pinoy National Rice Program | DA | Locally-funded | 7003.505 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 7676.135 | 6049.747 | 4612.767 | 843307 | 320677 | 62.4927 | Behind Schedule
162004070200002 | SOCSKSARGEN Area Development Program (included integrated food security program) | DA | Locally-funded | 1412 | 2011-01-01 | 2016-12-31 | Agriculture, Agrarian Reform and Natural Resources | 12 | 1263, 1247,1265 | 126303 | Ongoing | 352.59 | 292.304 | 27.578 | 53 | 53 | 90.9705 | Behind Schedule | Limited manpower at the Local Government Unit (LGU) level which causes delay in the timely conduct of site survey and preparation of Program of Works and Plans and Detailed Engineering. | LGU capacity
DA002 | Upgrading/Rehabilitation of Regional Fishport Complex | DA | Locally-funded | 534 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 723.857 | 215.2986 | 183.229 | 5 | 0 | 0 | Behind Schedule
162003010100000 | Formulation and Monitoring of ENR Sector Policies, Plans, Programs and Projects (includes all sectors and Management of Forestland and Forest Resources and Forest Boundary Delineation and Land Use Allocation) | DENR | Locally-funded | 3127.604 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
000003030100000 | Enforcement of Laws, Rules and Regulations: Permit issuance and monitoring of forest and forest resource use; Operations against illegal environment and natural resources activities (formerly Forest Protection) | DENR | Locally-funded | 4908.985 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
162003020100000 | Forest Development, Rehabilitation and Protection (a restructured PAP from Forest Development/National Greening Program, Community-Based Forestry Program and Soil Conservation and Watershed Management) | DENR | Locally-funded | 41094.186 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
164003010200000 | Geosciences Development Service [formerly Detailed Geohazard Assessment and Mapping] | DENR | Locally-funded | 1924.063 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | #N/A
162003020200000 | Land Survey, Disposition and Records Management (A restructured PAP from Land Management Services, Land Surveys - Cadastral, Field Network Survey, Survey of Foreshore, Reservation & Patrimonial Properties and Land Records Management) | DENR | Locally-funded | 8583.748 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
184003020300003 | Management of Coastal and Marine Resources/Areas (formerly Coastal and Marine Resources Management) | DENR | Locally-funded | 4191.208 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | #N/A
103003010200000 | Topographic Base Mapping and Geodetic Surveys (Mapping and Remote Sensing) | DENR | Locally-funded | 2441.148 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
224003020500000 | Family Health and Responsible Parenting Program | DOH | Locally-funded | 3274 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
000003020900000 | Health Facilities Enhancement Program | DOH | Locally-funded | 13271 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
226003020300001 | National Health Insurance Program | DOH | Locally-funded | 37060.44 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 37060.44 |  |  | 11581387 | 11466437 | 99.0075 | On-schedule | Limitation in the identification of the poor | Demand/identification/ processing/approval of demand-driven facilities/ sub-projects
224003020400008 | National TB Control Program | DOH | Locally-funded | 1090 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0
224003020400009 | Other Infectious Disease control incl HIV prevention | DOH | Locally-funded | 2916 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
224003020100002 | Rural Health Practice Program (Doctors to the Barrios, RN-HEALS, Midwives) | DOH | Locally-funded | 4256 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
165003012700002 | Laoag City Bypass Link Road Project | DPWH | Locally-funded | 1508 | 1905-07-04 | 1905-07-08 | Infrastructure Development | 1 | 128 |  | Ongoing | 1508 | 204.9 | 404.9 | 3048 | 3048 | 94 | Behind Schedule
165002000400218 | National Sewerage and Septage Management Program | DPWH | Locally-funded | 1085 | 1905-07-04 |  | Infrastructure Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing
287003020600000 | Pantawid Pamilyang Pilipino Program | DSWD | Locally-funded | 62322.89 | 1905-06-30 | 1905-07-08 | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 27193.0832 | 25925.7334 | 40342.4148 | 7789281 | 8800885 | 112.9871 | Ahead of Schedule | Lack of Supply Side. It serves as the major challenge that the program needs to address.
282003020900000 | Social Pension for Indigent Senior Filipino Citizens | DSWD | Locally-funded | 5962.628 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 5962.628 | 4050.7856 | 797.0887 | 3304001 | 1718780 | 52.0212 | Behind Schedule | Lack of computer equipment for the additional manpower in all Field Offices, Lack of bonded staff in the Field Offices to do the cash pay-out. | PMO manpower/capacity
284003020700000 | Supplementary Feeding Program | DSWD | Locally-funded | 3360.383 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 1931.4957 | 1931.4957 |  | 562262 | 0 | 0 | Behind Schedule
000003021000000 | Sustainable Livelihood Program | DSWD | Locally-funded | 4932.977 | 2011-01-01 |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 4072.216 | 2569.9822 | 2165.2931 | 395431 | 585689 | 148.1141 | Ahead of Schedule | The first quarter of 2015 for SLP has shown to be slow and steady marked by the almost 8 percent accomplishment against the 2015 targets by the quarter’s end. This is primarily expected since the first few months of 2015 served as the preparatory months for the Field Offices in terms of identifying the most appropriate projects for the target participants. The start of implementation for most of these projects is expected to start in the second quarter.
161004070500004 | Shared Service Facilities | DTI | Locally-funded | 1540 | 1905-07-05 |  | Industry, Trade and Tourism | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 1540 | 963.9128 | 1214.2625 | 1162 | 1305 | 112.3064 | Ahead of Schedule | Non-operating SSFS in Leyte due to damages caused by Typhoon Yolanda, Long procurement Process, Insufficient number of suppliers participating in the bidding process | Procurement, Sustainability and O&M
MMD001 | Rehabilitation and Upgrading of 12 Pumping Stations | MMDA | Locally-funded | 1600 | 1905-07-05 | 1905-07-07 | Infrastructure Development | 13 |  |  | Ongoing | 0 | 0 | 0 | 100 | 74 | 74 | Behind Schedule | The timing of project implementation that covers wet months wherein various weather disturbances caused the suspension of works in the project. | Adverse weather conditions
291004100100001 | PAyapa at Masaganang PamayaNAn (PAMANA) Program (in partnership with LGUs, DILG, DSWD, DAR, DA, DENR, DOE, NEA, NIA, DPWH, ARMM (ORG and Regional Line Agencies), NCIP, CHED, PHIC) | OPAPP | Locally-funded | 8402.1954 | 1905-07-03 | 1905-07-08 | Governance and Institutions Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing
291004141100002 | Socio Economic Component of the Normalization Process | OPAPP | Locally-funded | 2488.686 | 1905-07-07 | 1905-07-08 | Governance and Institutions Development | 15, 9, 12 |  |  | Ongoing | 2488.686 | 197.4 | 3.973 | 16500 | 2828 | 31.5083 | Behind Schedule | Problem 1: Submission of list of beneficiaries is dependent on the political track or passage of the BBL. Until BBL is passed the MILF will not decommission its combatants as the program for normalization in the annex on normalization of CAB laid the gradual process commensurate to its milestone. Thus, delivery of socio-econ package will only progress upon commencement of the decommissioning process. | Support from/coordination with stakeholders/ implementing partners
MMD002 | Installation of Intelligent Transport System | MMDA | Locally-funded | 3072.25 |  |  | Infrastructure Development | 13 |  |  | Ongoing | 0 | 0 | 0 | 93 | 93 | 100 | On-schedule | The project had difficulty in securing funding. With the on-going implementation of the phases, there are barangays that require permit (e.g. excavation permit) with fees charged. | Application/processing/ issuance of clearances/permits/ certificates/approvals from other government offices/agencies/bodies
163004040100002 | Barangay Line Enhancement Program | NEA | Locally-funded | 400 | 1905-07-03 | 1905-07-08 | Infrastructure Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 1660 | 982.2401 | 0 | 338 | 294 | 86.9822 | Behind Schedule
163004040100001 | Sitio Electrification Program | NEA | Locally-funded | 1500 | 1905-07-03 | 1905-07-08 | Infrastructure Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 7858 | 7830.934 | 5550.818 | 10530 | 14065 | 133.5708 | Ahead of Schedule
286004010600001 | Housing program for Informal Settler Families Living Along Danger Areas in Metro Manila | NHA | Locally-funded | 29188.795 | 1905-07-04 | 1905-07-08 | Social Reform and Community Development | 13 |  |  | Ongoing | 27971.275 | 25524.969 | 14771.563 | 78732 | 79395 | 100.8421 | On-schedule
165004030100002 | Bicol Int'l Airpot Development Project | DOTC | Locally-funded | 5635 | 2013-11-13 | 2015-05-06 | Infrastructure Development | 5 | 505 |  | Ongoing |  | 708 |  | 0 |  | 0
165004030300056 | Busuanga Airport Development Project | DOTC | Locally-funded | 16 | 2015 | 2017 | Infrastructure Development | 17 | 1753 |  | Ongoing |  | 0 |  | 0 |  | 0
165004030200011 | Line 1 and Line 2 System Rehabilitation Project | DOTC | Locally-funded | 12656.66 | 2011 | 2020 | Infrastructure Development | 13 |  |  | Ongoing |  | 0 |  | 0 |  | 0
165004030200002 | LRT Line 1 North Extension - Common Station Project | DOTC | Locally-funded | 1399.65 | 2014 | 2017 | Infrastructure Development | 13 |  |  | Ongoing | 0 | 0 | 0
165004100100013 | MRT 3 Capacity Expansion Project | DOTC | Locally-funded | 3769.38 | Feb 13 | Dec 16 | Infrastructure Development | 13 |  |  | Ongoing | 0 | 0 | 0
165004030100006 | Tacloban Airport Redevelopment Project | DOTC | Locally-funded | 493 | 2014-03-07 | Apr 2015 | Infrastructure Development | 8 | 837 |  | Ongoing |  | 13.67 |  | 0 |  | 0
DOT001 | Upgrading of Port Facilities: CAPEX/RM Project | DOTC | Locally-funded | 3015 |  |  | Infrastructure Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
203004060100001 | Provision for Potable Water Supply-Bottom-up Budgeting Process (BuB) Water Areas | DILG | Locally-funded | 2890.47 |  |  | Infrastructure Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 6192.855 | 3230.88 | 2522.91 | 2606 | 1878 | 72.3658 | Behind Schedule | Compliance to SGH and other governance requirements
203004060100002 | Sagana at Ligtas na Tubig sa Lahat (SALINTUBIG) Program | DILG | Locally-funded | 1572.73 | 1905-07-03 | 1905-07-08 | Infrastructure Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 3640.44 | 1916.75 | 1473 | 1354 | 1006 | 79.8092 | Behind Schedule | Political conflict is one of the major causes of delay, Natural calamities damaged some of the SALINTUBIG water system projects, Acquisition of Land, unavailability of water source, failure of bidding are some of the causes of delay, Absorptive Capacity of LGUs to implement water supply and regular projects, Fund allocation not sufficient to the actual requirement of the water supply program. | LGU capacity
241004090300004 | Recovery Assistance on Yolanda (RAY) | DILG | Locally-funded | 4012 | 1905-07-06 | 1905-07-08 | Governance and Institutions Development | 17, 5, 6, 7, 8 |  |  | Ongoing | 4012 | 2688.486 | 2572.249 | 0 | 339 | 0 |  | Difficulty in securing BBB standards, Delayed in project implementation due to procurement issues and changes/revisions in the scope of work, Lack and limited number oftechnical manpower in the LGUs and in the DILG Regional and Provincial Offices, Lack of available construction materials available at a time when the demand is so high because rehabilitation in the vast geographical area happened all at the same time.
DIL001 | BFP Service Establishment Project (SEP) | DILG | Locally-funded | 2742.39 |  |  | Governance and Institutions Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 2400 | 2400 | 2400
DIL002 | Conduct of Degree Program in Public Safety Education | DILG | Locally-funded | 526.8411 |  |  | Governance and Institutions Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 115.6426 | 115.6426 | 115.6426
144004010500001 | Construction of Jail Offices and Facilities | DILG | Locally-funded | 1398.215 |  |  | Governance and Institutions Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
DIL003 | Construction of PPSC facilities to improve the learning environment for uniformed personnel | DILG | Locally-funded | 196.16 |  |  | Governance and Institutions Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13 |  |  | Ongoing | 0 | 0 | 0
269003010200000 | Education and Training Program for Uniformed Personnel of the PNP, BFP, BJMP and other Public Safety Agencies | DILG | Locally-funded | 402.9381 |  |  | Governance and Institutions Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 139.8691 | 139.8691 | 139.8691 | 33850 | 44320 | 130.9306 | Ahead of Schedule
DIL004 | Establishment of ICT Capability for the Enforcement of the Fire Code (Fire Code Fees Collection system) | DILG | Locally-funded | 250.001 |  |  | Governance and Institutions Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
DIL005 | Jail Capability Build Up Program (Purchase of Equipment i.e Firearms, STAR Team Equipments, Vehicles, Probatons, CCTV Set, etc) | DILG | Locally-funded | 530.8528 |  |  | Governance and Institutions Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 265.5467 | 242.5003 | 105.1644
109003010200000 | Performance Challenge Fund | DILG | Locally-funded | 1003.7 | 1905-07-02 |  | Governance and Institutions Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 4014.1 | 2819.2381 | 2723.9389 | 502 | 41 | 8.1673 | Behind Schedule | Delayed released of FY 2014 PCF due a negative list status (needing clearance) | Budget and funds flow
103004100100001 | Support to Bottom-Up Budget Process and Empowerment Fund | DILG | Locally-funded | 250 | 1905-07-04 | 1905-07-08 | Governance and Institutions Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 55.8487 | 2.6001 | 58.4487 | 1634 | 1590 | 64.3268 | Behind Schedule | Low absorptive capacity of LGUS - limited number of technical staff to comply with the too many documentary requirements of the project | LGU capacity
DIL006 | BFP Service Upgrading and Modernization Program (SUMP) | DILG | Locally-funded | 10979.4751 |  |  | Governance and Institutions Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
201004010600004 | Resettlement Program a: for Informal Settler Families affected by Infrastructure Projects in Metro manila and those living along Danger Areas in nearby Provinces b. Regional Resettlement Program | NHA | Locally-funded | 15487.6 | 1905-07-03 | 1905-07-08 | Social Reform and Community Development | 13, 3, 4 | 458, 434, 314, 354, 308 |  | Ongoing
286004010600003 | Housing Assistance Program for Calamity Victims | NHA | Locally-funded | 30813.038 | 1905-07-03 | 1905-07-08 | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 30646.69 | 28611.215 | 6563.589 | 235688 | 312461 | 132.574 | Ahead of Schedule
NHA001 | Settlement Upgrading Program | NHA | Locally-funded | 127.845 | 1905-07-03 | 1905-07-08 | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 127.845 | 10.281 | 4.449 | 10728 | 9264 | 86.3535 | Behind Schedule
286004010600002 | AFP/PNP Housing Program | NHA | Locally-funded | 20870.32 | 1905-07-03 | 1905-07-08 | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 20870.32 | 15543.596 | 11482.859 | 90137 | 64876 | 71.9749 | Behind Schedule
286002000100000 | Local Housing Programs | NHA | Locally-funded | 3000 | 1905-07-03 | 2016 | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 939.664 | 760.229 | 716.58 | 4946 | 5532 | 111.848 | Ahead of Schedule
162004060400009 | Casecnan Multi-Purpose Irrigation and Power Project- Irrigation Component, Phase II | NIA | Locally-funded | 5445 | 1905-07-04 | 1905-07-08 | Agriculture, Agrarian Reform and Natural Resources | 3 | 349 |  | Ongoing | 4039.778 | 3316.697 |  |  |  | 88.43 |  | Delayed completion of CY 2014 POW and late start up of CY 2015 POW due to late release of project funds from DBM. | Budget and funds flow
DPW001 | 5 Billion Flood Control Projects | DPWH | Locally-funded | 3415.952 | 2013-01-01 | 2015-10-01 | Infrastructure Development | 13, 3, 4 | 354, 314 |  | Ongoing | 3415.952 | 3144.3182 | 2906.7331
165005050100011 | Baler-Casiguran Road Improvement Project | DPWH | Locally-funded | 1094.806 | 1905-07-05 | 1905-07-07 | Infrastructure Development | 3 | 377 |  | Ongoing | 0 | 0 | 0
162004060400010 | Balog-balog Multipurpose Project Phase II | NIA | Locally-funded | 13370 | 1905-07-05 | 1905-07-09 | Agriculture, Agrarian Reform and Natural Resources | 3 | 369 |  | Ongoing | 6532.99 | 532.99 | 532.99 | 0 | 0 | 17.79 | Behind Schedule | Delayed confirmation and approval of the Project by the NEDA Board. | Pending ICC approval/NEDA board confirmation or agency submission of ICC requisite documents for project restructuring (change in scope, loan extension, etc.)
162004060400042 | Umayam River Irrigation Project | NIA | Locally-funded | 1402.104 | 1905-07-04 | 1905-07-08 | Agriculture, Agrarian Reform and Natural Resources | 16 | 1603 |  | Ongoing | 1224.072 | 1034.203 | 205.5272 | 730 | 290 | 35.09 | Behind Schedule | Delayed procurement of civil work contracts due to prolong process in securing necessary pre-project implementation requirements such as loan financing (the project was previously proposed for possible ODA finacing), Environmental Compliance Certificate, Free and Prior Informed Consent (FPIC) document, Special Cutting Permits, etc. | Procurement
162004060400038 | Malitubog- Maridagao Irrigation Project, Stage 2 | NIA | Locally-funded | 4942.31 | 1905-07-03 | 1905-07-08 | Agriculture, Agrarian Reform and Natural Resources | 15, 12 | 1538, 1247 |  | Ongoing | 2241.35 | 2135.965 | 1381.873 | 4721 | 3340 | 77.17 | Behind Schedule | Delayed project completion attributed by the prolong process in securing loan financer for the project was originally proposed for ODA loan financing. | Pending ICC approval/NEDA board confirmation or agency submission of ICC requisite documents for project restructuring (change in scope, loan extension, etc.)
165003011200004 | Sen. Gil Puyat Avenue/Makati Avenue-Paseo de Roxas Vehicles Underpass Project | DPWH | Locally-funded | 1011.824 | 2015-02-01 | 2016-11-01 | Infrastructure Development | 13 | 137602 |  | Ongoing | 0 | 0 | 0 | 880.02 | 0 | 0 | Behind Schedule | Non-issuance of Makati City Government of Excavation Permit wherein 25% cash bond is required. | Application/processing/ issuance of clearances/permits/ certificates/approvals from other government offices/agencies/bodies
DPW002 | Water Supply, Sewerage and Sanitation Projects to Strategic Tourist Destinations | DPWH | Locally-funded | 1730.128 | 2014-01-01 | 2014-12-01 | Infrastructure Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
DPW003 | Bicol River Basin and Watershed Management Project | DPWH | Locally-funded | 5705 | 1905-06-29 | 1905-07-22 | Infrastructure Development | 5 | 516, 517, 505 |  | Ongoing | 3880 | 3076.2443 | 2662.9346 | 81 | 65 | 80.2469 | Behind Schedule | Right-of-way acquisition of the Quinale-Talisay Diversion Channel not yet funded. | Right-of-way and resettlement
165003011200003 | Bonifacio Global City- Ortigas Center Link Road Project (Phase I) | DPWH | Locally-funded | 1665 | 2015-05-01 | 2017-04-01 | Infrastructure Development | 13 | 137607, 137403 |  | Ongoing | 0 | 0 | 0 |  |  |  |  | Objection of the stakeholders of Brgy. Kapitolyo, Pasig City to implement the whole project. | Support from/coordination with stakeholders/ implementing partners.
165003010900002 | Widening of General Luis Street | DPWH | Locally-funded | 2547 | 2017-06-01 | 2019-01-01 | Infrastructure Development | 13 | 137404, 137501, 137504 |  | Ongoing | 0 | 0 | 0
DOE001 | Capacity Recovery and Uprating of Agus 6 Hydroelectric Power Units 1 and 2 | DOE | Locally-funded | 1590.5593 | 1905-07-06 | 1905-07-08 | Infrastructure Development | 10 |  |  | Ongoing
166004100100004 | Free Internet Wi-Fi Connectivity in Public Places | DOST | Locally-funded | 1408.669 | 1905-07-07 | 1905-07-10 | Infrastructure Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 1408.669 | 20.222 | 13.99 | 947 | 0 | 0 | Behind Schedule | Non-release of funds, Dredging of the Navigational Channel has still not commenced yet since the requirements of its NEDA-ICC approval, such as the ECC and Feasibility Study, are still pending. | Pending ICC approval/NEDA board confirmation or agency submission of ICC requisite documents for project restructuring (change in scope, loan extension, etc.)
DA003 | Implementation of Various Programs/Projects of Local Governments: Bottom-Up Budgeting (BUB) | DA | Locally-funded | 11850 |  |  | Agriculture, Agrarian Reform and Natural Resources | 13, 14, 1, 2, 3, 4, 17, 5, 6, 7, 8, 9, 10, 11, 12, 16 |  |  | Ongoing | 4659.34 | 3791.025 | 1200.589 | 4126 | 1426 | 43.3579 | Behind Schedule
165004070200010 | Farm-to-Market Roads | PCA | Locally-funded | 1500 |  | 1905-07-07 | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing |  |  |  | 150 | 150 | 100 | On-schedule
162004070200003 | KAANIB Enterprise Development Project | PCA | Locally-funded | 1621.21 | 1905-07-02 | 1905-07-07 | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing |  |  |  | 1847 | 2207 | 119.4911 | Ahead of Schedule | Failure of Bidding | Procurement
TES001 | Training for Work Scholarship Program | TESDA | Locally-funded | 2000 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 2000 | 1898.083 | 328.927 | 2007264 | 2198550 | 112.8561 | Ahead of SChedule | The need to enhance the employability of TWSP graduates. | Project design issues
292004140800002 | National Household Targeting System for Poverty Reduction (NHTS-PR) | DSWD | Locally-funded | 2069.001 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 126.458 | 57.1748 |  | 11487074.25 | 27386877 | 238.4147 | Ahead of Schedule
DOL001 | Special Program for Employment of Students (SPES) | DOLE | Locally-funded | 4632.273 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
DOL002 | DOLE Integrated Livelihood Programs (DILP) | DOLE | Locally-funded | 2609.282 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
DOL003 | Convergence Program to Address Child Labor (HELP ME) | DOLE | Locally-funded | 3500 |  |  | Social Reform and Community Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
103004090400001 | Unified Mapping Project | DENR | Locally-funded | 2196 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
183003010500001 | Implementation of Clean Air Regulations | DENR | Locally-funded | 2527.682 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
181003010600001 | Implementation of Ecological Solid Waste Management Regulations | DENR | Locally-funded | 2472.508 |  |  | Agriculture, Agrarian Reform and Natural Resources | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
000003030800000 | Construction/Improvement of Access Roads Leading to Airports, Seaports and Declared Tourism Destinations | DPWH | Locally-funded | 35753.984 |  |  | Infrastructure Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
162004060400014 | Quipot Irrigation Project | NIA | Locally-funded | 999.5 | 1905-07-04 | 1905-07-08 | Agriculture, Agrarian Reform and Natural Resources | 4 |  |  | Ongoing | 764.3 | 664.3 | 325.2924 | 1114 | 0 | 72.09 | Behind Schedule | Delayed completion of Contract No. QIPDC1 due to issued contract suspension due to lack of project endorsement by the RDC. Contract suspension started in September 15, 2014 and was lifted only on December 23, 2014. | Application/processing/ issuance of clearances/permits/ certificates/approvals from other government offices/agencies/bodies
000003020500000 | Flood Control Structures along Major River Basins and Principal River/ Basins | DPWH | Locally-funded | 16900 |  |  | Infrastructure Development | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 |  |  | Ongoing | 0 | 0 | 0
165003030800190 | Tangub City-Bonifacio-Don Victorino Road, Misamis Occidental, Zamboanga Del Norte | DPWH | Locally-funded | 1141.056 |  |  | Infrastructure Development | 9, 10 |  |  | Ongoing | 0 | 0 | 0
DPW004 | Iligan-Aurora Road, (Linamon-Lala Section) Lanao Del Norte | DPWH | Locally-funded | 1959.753 |  |  | Infrastructure Development | 10 |  |  | Ongoing | 0 | 0 | 0
DPW005 | Davao City-Digos Road, Davao-Cotabato Road, Davao | DPWH | Locally-funded | 1703.242 |  |  | Infrastructure Development | 11 |  |  | Ongoing | 0 | 0 | 0
292004060400059 | Malinao Dam Improvement Project | NIA | Locally-funded | 651.464 | 1905-07-07 | 1905-07-09 | Agriculture, Agrarian Reform and Natural Resources | 7 | 712 |  | Ongoing | [7 empty] | Lack of RDC endorsement and finalization of dam detailed design. | Project design issues
DPW006 | Capas-Botolan Road Zambales and Tarlac | DPWH | Locally-funded | 300 | 1905-07-08 | 1905-07-09 | Infrastructure Development | 3 | 369, 371 |  | Ongoing | 0 | 0 | 0
DPW007 | Sn. Nicolas-Solsona-Cabugao- Conner- Abbut Road, Pangasinan, Kalinga, Apayao | DPWH | Locally-funded | 5283.502 |  |  | Infrastructure Development | 1, 14 |  |  | Ongoing | 0 | 0 | 0
DPW008 | Gurel-Bokod-Kapangan- Buguias Road, Benguet | DPWH | Locally-funded | 1250 |  |  | Infrastructure Development | 14 |  |  | Ongoing | 0 | 0 | 0
DPW009 | Acop-Kapangan-Kibungan Road, Benguet | DPWH | Locally-funded | 3340 |  |  | Infrastructure Development | 14 |  |  | Ongoing | 0 | 0 | 0
DPW010 | Siquijor Circumferential Road Siquijor | DPWH | Locally-funded | 1153 |  |  | Infrastructure Development | 7 |  |  | Ongoing | 0 | 0 | #N/A
DPW011 | Guimaras Circumferential Road Guimaras | DPWH | Locally-funded | 1438.336 |  |  | Infrastructure Development | 6 |  |  | Ongoing | 0 | 0
DPW012 | Toledo-Tabuelan-San Remigio Road, Cebu | DPWH | Locally-funded | 2440.22 |  |  | Infrastructure Development | 7 |  |  | Ongoing | 0 | 0 | 0
DPW013 | Bacolod-Murcia-Benedicto-San Carlos Road, Negros Occidental | DPWH | Locally-funded | 1090.12 |  |  | Infrastructure Development | 6 |  |  | Ongoing | 0 | 0 | 0
DPW014 | San Emilio-Quirino-Cervantes Road, Ilocos Sur | DPWH | Locally-funded | 1829.64 |  |  | Infrastructure Development | 1 |  |  | Ongoing | 0 | 0 | #N/A
DPW015 | Kalinga-Abra Rd (Bangued-Lubuagan Section) Abra, Kalinga | DPWH | Locally-funded | 2816.89 |  |  | Infrastructure Development | 14 |  |  | Ongoing | 2816.89 | 2056.29 | 0 | 83.394 | 35.564 | 42.6458 | Behind Schedule
165003015300062 | Cagayan de Oro Bypass Road, Misamis Oriental | DPWH | Locally-funded | 1220 |  |  | Infrastructure Development | 10 |  |  | Ongoing | 0 | 0 | 0
292004060400057 | Upper Butique SRIP | NIA | Locally-funded | 2041.414 | 1905-07-02 | 1905-07-09 | Agriculture, Agrarian Reform and Natural Resources | 14 | 1444 |  | Ongoing | 96.889 | 96.89 | 96.89 | 0 | 0 | 76.63 | Behind Schedule | Awaiting finalization of reformulated Feasibility Study and Detailed Design for the dam construction. | Project design issues
146004100400001 | National Justice Information System | DOJ | Locally-funded | 1809.404 | 1905-07-07 | 1905-07-10 | Governance and Institutions Development | 13 |  |  | Ongoing | 187.421 | 131.727 | 33.845 | 225 | 117 | 38.4667 | Behind Schedule | Interagency coordination constraints, Changes in leadership, Unsustained and/or inadequate funding, Hardware and internet availability, Delays in procurment process, Inadequate manpower and capacity among implementing/participating agencies. | Support from/coordination with stakeholders/ implementing partners, PMO manpower/ capacity, Budget and funds flow, Sustainability and O&M, Procurement.